## Instructions
Stakeholder Engagement Assessment Matrix — Filled Example
Use stakeholder identifiers rather than personal names where appropriate, restrict sensitive judgments, and follow organizational access policy.
Topic | Guidance
Purpose | Compare current and desired stakeholder engagement states and record evidence, actions, ownership, and review cadence.
C and D | C marks current engagement; D marks desired engagement; C/D means the current and desired states are the same.
Privacy | Use stakeholder identifiers rather than personal names where appropriate, restrict sensitive judgments, and follow organizational access policy.
Allowed states | Unaware, Resistant, Neutral, Supportive, Leading. Organizations may tailor labels when the tailored meanings are documented.
Authority boundary | This is an assessment tool / working artifact, not the formal output of Plan Stakeholder Engagement and not a universal approval record.
Blank versus filled | The blank workbook contains structure, definitions, formulas where useful, and no stakeholder records. The filled workbook uses fictional stakeholder IDs only.
Source | PMI Authorized PMP Exam Prep Learner Handout Lesson 3, July 2026, PDF pages 7, 12, 14, 20–24, and 99–104; matrix example on page 104.
Template disclaimer | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Engagement Matrix
Stakeholder Engagement Assessment Matrix — Engagement Matrix
Text markers communicate state without relying on color. C = current; D = desired; C/D = same state.
Stakeholder ID | Unaware | Resistant | Neutral | Supportive | Leading

## Stakeholder Detail
Stakeholder Engagement Assessment Matrix — Stakeholder Detail
Use stakeholder identifiers rather than personal names where appropriate, restrict sensitive judgments, and follow organizational access policy.
Project | Stakeholder ID | Role or group | Current state | Desired state | Observed evidence | Engagement gap | Recommended engagement action | Owner | Review date | Next review date | Template note
ServiceBridge Modernization | STK-01 | Sponsor | Supportive | Leading | Approves direction and removes funding barriers but delegates most advocacy. |  | Sponsor the next governance briefing and reinforce the service outcome with functional leaders. | Service Modernization Program Manager | 2026-10-15 | 2026-11-12 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-02 | Customer-service director | Leading | Leading | Leads operational design decisions and actively recruits subject-matter participation. |  | Maintain direct decision access and confirm benefit-measure readiness. | Service Modernization Program Manager | 2026-10-15 | 2026-11-12 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-03 | Compliance lead | Neutral | Supportive | Reviews evidence when asked but has not joined release-readiness planning. |  | Schedule an evidence-planning session and agree review checkpoints before the next release gate. | Service Modernization Program Manager | 2026-10-15 | 2026-10-29 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-04 | Support-team representative | Resistant | Supportive | Raises credible concerns about workload, training time, and unresolved support procedures. |  | Run a support-workflow walkthrough, record issues, and co-design the training and escalation path. | Customer-service director | 2026-10-15 | 2026-10-29 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-05 | External implementation seller | Neutral | Supportive | Meets contractual reporting obligations but contributes limited integration-risk insight. |  | Add a joint dependency review and clarify escalation expectations within the agreement. | Service Modernization Program Manager | 2026-10-15 | 2026-11-05 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-06 | Frontline user representative | Unaware | Supportive | Has not yet seen the appointment workflow or the accessibility acceptance approach. |  | Invite the representative to a guided demonstration and capture feedback before backlog refinement. | Product Owner | 2026-10-15 | 2026-10-29 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Engagement Actions
Stakeholder Engagement Assessment Matrix — Engagement Actions
Actions implement strategy; the matrix itself does not contain the complete Stakeholder Engagement Plan.
Action ID | Stakeholder ID | Action | Owner | Due date | Status | Evidence of result
EA-001 | STK-01 | Sponsor the next governance briefing and reinforce the service outcome with functional leaders. | Service Modernization Program Manager | 2026-11-12 | Not started
EA-002 | STK-02 | Maintain direct decision access and confirm benefit-measure readiness. | Service Modernization Program Manager | 2026-11-12 | Not started
EA-003 | STK-03 | Schedule an evidence-planning session and agree review checkpoints before the next release gate. | Service Modernization Program Manager | 2026-10-29 | Not started
EA-004 | STK-04 | Run a support-workflow walkthrough, record issues, and co-design the training and escalation path. | Customer-service director | 2026-10-29 | Not started
EA-005 | STK-05 | Add a joint dependency review and clarify escalation expectations within the agreement. | Service Modernization Program Manager | 2026-11-05 | Not started
EA-006 | STK-06 | Invite the representative to a guided demonstration and capture feedback before backlog refinement. | Product Owner | 2026-10-29 | Not started

## Change History
Stakeholder Engagement Assessment Matrix — Change History
Record material reassessments and review dates; do not treat every attitude change as a formal change request.
Version | Change date | Changed by role | Summary | Next review
1.0 | 2026-10-15 | Service Modernization Program Manager | Initial fictional engagement assessment | 2026-10-29

## State Definitions
Stakeholder Engagement Assessment Matrix — State Definitions
States describe engagement toward the project or change. Organizations may tailor labels and definitions.
State | Definition | Does not mean
Unaware | The stakeholder does not know about the project or its potential effects. | A measure of low authority or influence
Resistant | The stakeholder knows about the project but opposes it, its effects, or the proposed change. | A measure of low power or bad character
Neutral | The stakeholder is aware but is neither actively supportive nor actively resistant. | A requirement to ignore the stakeholder
Supportive | The stakeholder supports the project or change and may assist its success. | Formal approval authority
Leading | The stakeholder is actively engaged in helping the project succeed and influencing others positively. | Project-management or organizational authority