## Instructions
ServiceBridge Modernization — Adaptive Metrics
Topic | Guidance
Purpose | Editable, auditable ServiceBridge examples generated from definitions/adaptive-metrics.yaml.
Inputs | Blue-filled cells are editable inputs; formulas remain visible and no macros are used.
Velocity | Only Done items count. The 80%-complete item contributes zero. Story points are not hours or productivity.
Control chart | Limits are supplied illustrative inputs. No control-limit formula is published.
Sources | July 2026 PMI Lessons 5 and 7; Scrum Guide 2020; Kanban Guide May 2025.

## Velocity
ServiceBridge Modernization — Adaptive Metrics
Item / Sprint | Estimate / points | Status | Counts toward velocity
SB-101 | 8 | Done
SB-102 | 5 | Done
SB-103 | 13 | 80 percent complete
SB-104 | 3 | Done
Iteration velocity
Sprint | Completed points
1 | 21
2 | 25
3 | 23
4 | 27
5 | 20
6 | 28
Average first four
Remaining backlog | 100
Forecast Sprints

## Burndown
ServiceBridge Modernization — Adaptive Metrics
Period | Total scope | Completed | Remaining | Guideline only
0 | 100 | 0
1 | 100 | 16
2 | 115 | 28
3 | 115 | 45
4 | 130 | 61
5 | 130 | 82
6 | 130 | 108
7 | 130 | 130

## Burnup
ServiceBridge Modernization — Adaptive Metrics
Period | Total scope | Completed
0 | 100 | 0
1 | 100 | 16
2 | 115 | 28
3 | 115 | 45
4 | 130 | 61
5 | 130 | 82
6 | 130 | 108
7 | 130 | 130

## Cumulative Flow
ServiceBridge Modernization — Adaptive Metrics
Period | Ready | In Progress | Review | Done | Total
1 | 6 | 2 | 1 | 1
2 | 7 | 3 | 1 | 2
3 | 7 | 3 | 2 | 3
4 | 8 | 4 | 3 | 4
5 | 8 | 4 | 5 | 5
6 | 8 | 4 | 6 | 7
7 | 9 | 4 | 5 | 9
8 | 10 | 3 | 3 | 12

## Throughput
ServiceBridge Modernization — Adaptive Metrics
Completed items | Time periods | Period unit | Throughput
18 | 3 | week

## Lead and Cycle Time
ServiceBridge Modernization — Adaptive Metrics
Item | Request day | Work starts | Delivery day | Lead time | Cycle time | Convention
SB-118 | 0 | 2 | 5.5 |  |  | Working-day fractions; compatible finish point

## Control Chart
ServiceBridge Modernization — Adaptive Metrics
Observation | Cycle time | Mean | Supplied LCL | Supplied UCL
1 | 4 |  | 2 | 9
2 | 5 |  | 2 | 9
3 | 4 |  | 2 | 9
4 | 6 |  | 2 | 9
5 | 5 |  | 2 | 9
6 | 12 |  | 2 | 9
7 | 5 |  | 2 | 9
8 | 4 |  | 2 | 9

## Impediments
ServiceBridge Modernization — Adaptive Metrics
Description | Severity | Current action | Owner | Age days | Status
Test environment unavailable | High | Infrastructure escalation active | Platform Lead | 4 | Escalated
Vendor test account delayed | Medium | Confirm delivery date | Vendor Manager | 2 | Open

## Formula and Metric Reference
ServiceBridge Modernization — Adaptive Metrics
Metric ID | Preferred name | Type | Calculation | Units | Misuse warnings | Source IDs
ADM-VEL-001 | Velocity | iteration forecast | Velocity = sum of estimates for items completed to the agreed Definition of Done during the iteration | Team-specific estimate units per iteration, commonly story points per Sprint; story points are not hours. | Do not count partial work; Do not compare teams; Do not use for individual productivity; Do not impose a performance quota | SRC-PMI-COURSE-LESSON-5-2026; SRC-PMI-COURSE-LESSON-7-2026
ADM-THR-001 | Throughput | flow metric | Throughput = completed work items / time period | Items per stated time period. | Do not substitute story points; State the time period; Account for item-size variation | SRC-PMI-COURSE-LESSON-5-2026; SRC-PMI-COURSE-LESSON-7-2026; SRC-KANBAN-GUIDE
ADM-CYC-001 | Cycle Time | time measure | Cycle time = finish time - workflow start time | Elapsed calendar or working time under a stated convention. | Define both endpoints; Do not infer causation from an average alone | SRC-PMI-COURSE-LESSON-7-2026; SRC-KANBAN-GUIDE
ADM-LEAD-001 | Lead Time | time measure | Lead time = delivery time - defined request or commitment time | Elapsed calendar or working time under a stated convention. | Name the start convention; Do not compare incompatible endpoints | SRC-PMI-COURSE-LESSON-7-2026
ADM-WIP-001 | Work in Progress | flow metric | WIP = count of items started and not finished | Work items. | A limit without an explicit workflow policy is insufficient | SRC-PMI-COURSE-LESSON-7-2026; SRC-KANBAN-GUIDE
ADM-AGE-001 | Work Item Age | time measure | Work item age = current time - workflow start time | Elapsed time. | Age is a signal for investigation; not blame | SRC-KANBAN-GUIDE
ADM-BURN-001 | Burn Charts | cumulative measure | Remaining work = total scope - completed work | Consistent work units over time. | Do not hide scope change; Incomplete work remains in the total | SRC-PMI-COURSE-LESSON-5-2026; SRC-PMI-COURSE-LESSON-7-2026
ADM-CFD-001 | Cumulative Flow Diagram | cumulative measure | Each boundary equals the cumulative count at or beyond a workflow state | Work items over time. | One diagram does not prove a cause | SRC-PMI-COURSE-LESSON-5-2026; SRC-PMI-COURSE-LESSON-7-2026
ADM-BOARD-001 | Task Board or Kanban Board | visual-management tool | Not applicable | Work items by state. | Not every task board is a complete Kanban system | SRC-PMI-COURSE-LESSON-5-2026; SRC-PMI-COURSE-LESSON-7-2026; SRC-KANBAN-GUIDE
ADM-CONTROL-001 | Control Chart | process-stability measure | Mean = sum of observations / number of observations; control limits are supplied illustrative inputs, not calculated here. | Same unit as the plotted process measure. | Do not publish or infer an unsupported limit formula | SRC-PMI-COURSE-LESSON-7-2026
ADM-RAD-001 | Information Radiator | visual-management tool | Not applicable | Not applicable. | Visibility does not make stale information useful | SRC-PMI-COURSE-LESSON-5-2026; SRC-PMI-COURSE-LESSON-7-2026
ADM-IMP-001 | Impediment List and Visualization | impediment measure | Age = current date - identified date | Impediment count and elapsed age. | Scrum Master accountability does not mean personal removal of every impediment; Do not penalize a team for reporting impediments | SRC-PMI-COURSE-LESSON-5-2026; SRC-PMI-COURSE-LESSON-7-2026