## Event Summary
ServiceBridge Modernization — Scrum Events quick reference
Event | Purpose | Participants | Timing | Timebox | Typical result
Sprint | Create value through a usable Increment while progressing toward the Product Goal. | Scrum Team | A new Sprint begins immediately after the previous Sprint concludes. | Fixed length of one month or less. | Increment; Product Backlog
Sprint Planning | Decide why the Sprint is valuable, what can be completed, and how the selected work will be approached. | Entire Scrum Team | Starts the Sprint. | Maximum eight hours for a one-month Sprint. | Sprint Goal; Sprint Backlog
Daily Scrum | Inspect progress toward the Sprint Goal and adapt the immediate plan. | Developers | Every working day of the Sprint at the same time and place to reduce complexity. | Fifteen minutes. | Sprint Backlog
Sprint Review | Inspect the Sprint outcome with stakeholders and decide what to do next. | Scrum Team; Relevant stakeholders | Near the end of the Sprint before the Sprint Retrospective. | Maximum four hours for a one-month Sprint. | Product Backlog
Sprint Retrospective | Increase quality and team effectiveness. | Entire Scrum Team | Concludes the Sprint after the Sprint Review. | Maximum three hours for a one-month Sprint. | Sprint Backlog; Definition of Done

## Event Details
ServiceBridge Modernization — Scrum Events quick reference
Event | Inputs | What happens | Outputs or adaptations | Shorter-Sprint treatment | Hybrid treatment
Sprint | Product Goal; Product Backlog; Definition of Done | Create value through a usable Increment while progressing toward the Product Goal. | Increment; Product Backlog | The Sprint retains a fixed length of one month or less; the contained events are usually shorter. | The Sprint governs adaptive delivery work; project funding, contracts, external milestones, compliance, and transition dates remain in the surrounding governance model.
Sprint Planning | Product Goal; Product Backlog; Definition of Done | Decide why the Sprint is valuable, what can be completed, and how the selected work will be approached. | Sprint Goal; Sprint Backlog | Usually shorter for shorter Sprints. | The team plans Sprint work within project-level release, compliance, dependency, and milestone constraints.
Daily Scrum | Sprint Goal; Sprint Backlog | Inspect progress toward the Sprint Goal and adapt the immediate plan. | Sprint Backlog | The maximum remains fifteen minutes. | Project reporting consumes transparent Sprint information without turning the Daily Scrum into a manager-led status meeting.
Sprint Review | Product Goal; Product Backlog; Increment | Inspect the Sprint outcome with stakeholders and decide what to do next. | Product Backlog | Usually shorter for shorter Sprints. | Review feedback may adapt the Product Backlog but does not automatically approve baseline change or constitute contractual acceptance.
Sprint Retrospective | Sprint Goal; Sprint Backlog; Definition of Done | Increase quality and team effectiveness. | Sprint Backlog; Definition of Done | Usually shorter for shorter Sprints. | Team improvements enter the next Sprint while project-level lessons, quality, risk, and governance records remain coordinated separately.

## Roles and Participation
ServiceBridge Modernization — Scrum Events quick reference
Event | Product Owner | Scrum Master | Developers | Stakeholders | Hybrid project manager or governance
Sprint | Accountable Scrum Team member | Enables Scrum effectiveness; not task manager | Primary participants | Contextual, not mandatory | Consumes evidence and handles reserved decisions without becoming a fourth Scrum accountability
Sprint Planning | Accountable Scrum Team member | Enables Scrum effectiveness; not task manager | Primary participants | Contextual, not mandatory | Consumes evidence and handles reserved decisions without becoming a fourth Scrum accountability
Daily Scrum | Not the event's required participant | Enables Scrum effectiveness; not task manager | Primary participants | Contextual, not mandatory | Consumes evidence and handles reserved decisions without becoming a fourth Scrum accountability
Sprint Review | Accountable Scrum Team member | Enables Scrum effectiveness; not task manager | Primary participants | Participate in Sprint Review when relevant | Consumes evidence and handles reserved decisions without becoming a fourth Scrum accountability
Sprint Retrospective | Accountable Scrum Team member | Enables Scrum effectiveness; not task manager | Primary participants | Contextual, not mandatory | Consumes evidence and handles reserved decisions without becoming a fourth Scrum accountability

## Inputs and Outputs
ServiceBridge Modernization — Scrum Events quick reference
Practice | Type | Inputs | Inspected or adapted | Outputs
Sprint | official event container | Product Goal; Product Backlog; Definition of Done | Product Goal; Product Backlog; Sprint Goal; Sprint Backlog; Increment; Definition of Done | Increment; Product Backlog
Sprint Planning | official event | Product Goal; Product Backlog; Definition of Done | Product Goal; Product Backlog; Sprint Goal; Sprint Backlog | Sprint Goal; Sprint Backlog
Daily Scrum | official event | Sprint Goal; Sprint Backlog | Sprint Goal; Sprint Backlog | Sprint Backlog
Sprint Review | official event | Product Goal; Product Backlog; Increment | Product Goal; Product Backlog; Increment | Product Backlog
Sprint Retrospective | official event | Sprint Goal; Sprint Backlog; Definition of Done | Sprint Backlog; Definition of Done | Sprint Backlog; Definition of Done
Product Backlog refinement | ongoing activity not event | Product Goal; Product Backlog | Product Goal; Product Backlog | Product Backlog

## Common Exam Traps
ServiceBridge Modernization — Scrum Events quick reference
Topic | Trap | Correct distinction
Sprint | A Sprint is not merely a development phase | Protect the Sprint Goal and quality; clarify and renegotiate scope with the Product Owner as learning occurs.
Sprint | The Product Owner alone may cancel a Sprint when the Sprint Goal becomes obsolete | Protect the Sprint Goal and quality; clarify and renegotiate scope with the Product Owner as learning occurs.
Sprint Planning | The Product Owner does not assign Developers' detailed work, Developers are responsible for sizing their work | Remember the three topics: why valuable, what can be done, and how it will get done.
Daily Scrum | The old three-question format is optional | A manager asking each person for status is not the purpose of the Daily Scrum.
Daily Scrum | Product Owner or Scrum Master attendance does not make this their status meeting | A manager asking each person for status is not the purpose of the Daily Scrum.
Sprint Review | It is a working session rather than merely a demo | Focus on product outcome, Product Goal progress, environmental change, stakeholder feedback, and next steps.
Sprint Review | It is not automatically formal acceptance | Focus on product outcome, Product Goal progress, environmental change, stakeholder feedback, and next steps.
Sprint Retrospective | It is not a blame session or performance appraisal | Inspect people, interactions, processes, tools, and Definition of Done; select useful improvements.
Sprint Retrospective | It examines how the team works rather than stakeholder satisfaction with the product | Inspect people, interactions, processes, tools, and Definition of Done; select useful improvements.
Product Backlog refinement | Refinement is not an official Scrum event | Product Owner remains accountable for backlog management; Developers are responsible for sizing work.
Product Backlog refinement | A scheduled refinement meeting is a team practice rather than a Scrum requirement | Product Owner remains accountable for backlog management; Developers are responsible for sizing work.
Agile | Agile does not mean Scrum. | Name the framework when mechanics matter.
Kanban | Kanban does not require Scrum events. | Do not prescribe the Sprint cycle to a Kanban system.

## Hybrid Example
ServiceBridge Modernization — Scrum Events quick reference
Layer | ServiceBridge cadence | Connection rule | Does not replace
Project governance | Funding, contracts, release milestones, compliance obligations, transition dates, budget, vendor, risk, and governance reviews. | Scrum evidence informs project reporting; reserved baseline, contract, compliance, acceptance, and transition decisions remain with named authorities. | Scrum events or Developers' self-management
Scrum delivery | Sprint Planning, delivery with Daily Scrum, Sprint Review, Sprint Retrospective, and ongoing Product Backlog refinement. | Scrum evidence informs project reporting; reserved baseline, contract, compliance, acceptance, and transition decisions remain with named authorities. | Baseline change, contract authority, formal acceptance, or governance