## Instructions
Stakeholder Power–Interest Grid — Filled Example
Use identifiers rather than personal names where appropriate, document observable evidence, restrict sensitive judgments, and follow organizational access policy.
Topic | Guidance
Purpose | Classify stakeholders qualitatively by evidenced power and interest, then tailor engagement and communication.
Privacy | Use identifiers rather than personal names where appropriate, document observable evidence, restrict sensitive judgments, and follow organizational access policy.
Scoring boundary | Numeric scoring is an optional Atlas implementation aid, not a PMI-prescribed calculation and not required to use the grid.
Threshold | The included 3.0 threshold is an editable Atlas example and must be defined before assessment.
Source | PMI Authorized PMP Exam Prep Learner Handout Lesson 3, July 2026, PDF pages 7, 9, 15, and 16.
Disclaimer | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Power–Interest Grid
Stakeholder Power–Interest Grid — Assessment
Use identifiers rather than personal names where appropriate, document observable evidence, restrict sensitive judgments, and follow organizational access policy.
Project | Stakeholder ID | Role or group | Power evidence | Interest evidence | Power score | Interest score | Power level | Interest level | Assigned quadrant | Rationale | Communication approach | Engagement approach | Review date | Next review date | Template note
ServiceBridge Modernization | STK-01 | Sponsor | Controls funding and removes enterprise barriers | Reviews outcomes and advocates at governance forums | 5 | 5 | High | High |  | Strategic authority and active outcome ownership require direct engagement | Concise decision briefs plus immediate exception escalation | Prepare decisions jointly and use sponsor advocacy | 2026-10-15 | 2026-11-12 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-02 | Customer-service director | Owns operational design decisions and benefit measures | Leads workshops and recruits subject-matter participation | 4 | 5 | High | High |  | Operational authority and continuous involvement are both high | Weekly working review with direct decision access | Co-design operations and confirm benefit readiness | 2026-10-15 | 2026-11-12 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-03 | Compliance authority | Can withhold compliance approval at release gates | Focuses on evidence at defined control points | 5 | 3 | High | Low |  | Formal authority is high while day-to-day involvement is intentionally limited | Evidence summaries aligned to agreed checkpoints | Confirm criteria early and consult before release gates | 2026-10-15 | 2026-10-29 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-04 | Support-team representative | Advises workflow but does not approve the program | Is directly affected and participates actively in training design | 2 | 5 | Low | High |  | High operational impact and interest warrant feedback access despite limited authority | Regular workflow updates and visible issue responses | Co-design training and support escalation paths | 2026-10-15 | 2026-10-29 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-05 | External implementation seller | Controls specialist capacity and integration dependencies | Concentrates on contractual deliverables and escalations | 4 | 2 | High | Low |  | Dependency influence is high but broader project interest is limited | Contract-aligned dependency and exception reporting | Joint dependency reviews and clear escalation thresholds | 2026-10-15 | 2026-11-05 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | STK-06 | Frontline user representative | Advises product decisions without formal approval authority | Is directly affected and seeks accessible workflow outcomes | 2 | 5 | Low | High |  | Direct impact and feedback value make frequent participation useful | Demonstrations in accessible formats with feedback closure | Invite to reviews and backlog refinement | 2026-10-15 | 2026-10-29 | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Assessment Evidence
Stakeholder Power–Interest Grid — Evidence
Evidence comes before placement; scores are optional Atlas synthesis.
Stakeholder ID | Power indicator | Evidence | Score 1–5 | Interest indicator | Evidence | Score 1–5

## Communication Strategy
Stakeholder Power–Interest Grid — Communication Strategy
Tailor; quadrant labels are not automatic communication prescriptions.
Stakeholder ID | Quadrant | Information need | Method | Cadence | Owner | Feedback route

## Change History
Stakeholder Power–Interest Grid — Change History
Reassess when evidence or context changes.
Version | Review date | Changed by role | Evidence change | Placement change | Next review
1.0 | 2026-10-15 | Service Modernization Program Manager | Initial fictional assessment | Initial placement | 2026-10-29

## Scoring Definitions
Stakeholder Power–Interest Grid — Scoring Definitions
Numeric scoring is optional Atlas synthesis, not a PMI-prescribed calculation.
Type | Indicator or value | Definition
Status | atlas_optional_implementation | Numeric scoring is an optional Atlas implementation aid, not a PMI-prescribed calculation and not required to use the grid.
Threshold | 3 | Example only; document any tailored threshold before use.
Power | Decision authority | Rate 1–5 from evidence
Power | Resource control | Rate 1–5 from evidence
Power | Approval or acceptance authority | Rate 1–5 from evidence
Power | Ability to constrain or accelerate outcomes | Rate 1–5 from evidence
Interest | Degree affected | Rate 1–5 from evidence
Interest | Information demand | Rate 1–5 from evidence
Interest | Participation level | Rate 1–5 from evidence
Interest | Attention to outcomes | Rate 1–5 from evidence