## Start Here
ServiceBridge Modernization — illustrative Atlas working reference
Field | Guidance
Purpose | Tailor role, responsibility, authority, artifact ownership, handoff, and escalation decisions for ServiceBridge Modernization.
Status | Illustrative Atlas synthesis; not a prescribed organizational design.
How to use | Filter the reference sheets, then record scenario-specific assignments in Assignment Workshop and Decision & Escalation.
Authority rule | Responsibility, ownership, verification, acceptance, approval, and escalation are separate concepts.

## Role Registry
ServiceBridge Modernization — illustrative Atlas working reference
Role ID | Role | Family | Purpose | Authority | Boundary | Delivery context | Evidence status
ROL-SPONSOR | Sponsor | governance | Champions the intended outcome and connects the project to organizational direction. | Authorizes the project or phase and makes sponsor-level funding and direction decisions within the governing model. | Does not replace the project manager in day-to-day integration or the customer in formal acceptance unless explicitly assigned both roles. | Applies across predictive, adaptive, and hybrid delivery; cadence and delegated limits vary. | atlas_synthesis
ROL-GOVERNANCE-BOARD | Governance Board | governance | Provides collective oversight and decisions above delegated project authority. | Decides reserved funding, direction, risk-acceptance, and continuation matters defined by governance. | Does not perform team work or automatically act as the change control board. | Governs outcomes in any delivery approach without prescribing the team cadence. | atlas_synthesis
ROL-PROJECT-MANAGER | Project Manager | project | Integrates project work, information, decisions, and stakeholders within delegated authority. | Makes project decisions within the charter, plan, and delegated thresholds; routes reserved decisions. | Is not automatically the product owner, technical authority, acceptance authority, or sponsor. | More formally coordinating in predictive settings; often an integration and governance bridge in hybrid settings; may be absent or differently titled in adaptive product delivery. | atlas_synthesis
ROL-PMO | PMO or Portfolio Office | governance | Provides governance support, standards, assurance, and portfolio-level coordination. | Holds only the standards, assurance, or portfolio decision rights explicitly delegated to it. | Is not automatically the project sponsor or project manager. | May support predictive controls, adaptive governance, or hybrid integration. | atlas_synthesis
ROL-CUSTOMER | Customer or Acceptance Authority | value | Determines whether verified results satisfy agreed acceptance criteria. | Accepts or rejects deliverables within the applicable agreement and delegated acceptance scope. | Technical verification does not transfer this acceptance decision to the quality role. | Acceptance may occur at phase gates, releases, or increments; contractual authority remains explicit. | atlas_synthesis
ROL-PRODUCT-OWNER | Product Owner | scrum | Maximizes product value and manages the Product Backlog effectively. | Makes Product Backlog ordering decisions; the organization respects those decisions. | One accountable person in Scrum, not a committee; may delegate work but remains accountable and is not automatically the project sponsor or acceptance authority. | A Scrum accountability; hybrid governance must state how backlog authority connects to baselines, funding, contracts, and acceptance. | verified_official
ROL-SCRUM-MASTER | Scrum Master | scrum | Establishes Scrum and enables the Scrum Team to improve its effectiveness. | Facilitates and coaches Scrum use; does not assign work or own product decisions by virtue of the accountability. | Not the team manager, project manager, or Product Owner solely because of this accountability. | A Scrum accountability; in hybrid work it may coexist with project integration and governance roles. | verified_official
ROL-DEVELOPERS | Developers | scrum | Create a usable Increment each Sprint. | Self-manage how Sprint work is performed within the Product Goal, Sprint Goal, and Definition of Done. | The term is not limited to software developers and does not confer sponsor, product, or acceptance authority. | A Scrum accountability held by the people creating the Increment. | verified_official
ROL-DELIVERY-TEAM | Delivery Team | delivery | Produces and integrates project or product results. | Chooses working methods and makes technical or delivery decisions within delegated boundaries. | Does not automatically own product priority, formal acceptance, or reserved governance decisions. | Generic cross-approach term; use Scrum accountabilities when specifically describing Scrum. | atlas_synthesis
ROL-FUNCTIONAL-MANAGER | Functional or Resource Manager | delivery | Provides functional capability, people, and discipline oversight. | Controls resources and functional decisions to the extent assigned by the organization. | Does not own integrated project outcomes unless separately assigned. | Common in matrix and predictive organizations and may support adaptive teams. | atlas_synthesis
ROL-SUBJECT-MATTER-EXPERT | Subject-Matter Expert | delivery | Supplies specialized knowledge for analysis, design, estimates, and decisions. | Advises unless a specific technical or specialist approval right is delegated. | Expertise alone does not create project, product, or acceptance authority. | Applies across delivery approaches. | atlas_synthesis
ROL-QUALITY-AUTHORITY | Quality Authority | assurance | Establishes or applies quality controls and determines technical verification status. | Verifies or rejects technical conformity within delegated quality authority. | Verification is not customer acceptance and does not itself authorize baseline change. | May be an independent function, embedded specialist, or shared team responsibility depending on risk and governance. | atlas_synthesis
ROL-COMPLIANCE-AUTHORITY | Compliance Authority | assurance | Interprets applicable obligations and determines whether compliance evidence is sufficient. | Makes specialist compliance decisions and stop or escalation decisions only within delegated policy. | Does not waive legal or regulatory obligations outside its mandate. | Applies across approaches; evidence cadence may differ but obligations remain. | atlas_synthesis
ROL-CHANGE-AUTHORITY | Change Authority or CCB | governance | Decides controlled changes that exceed delegated delivery or project authority. | Decides changes within the thresholds reserved to the role or board. | Does not decide ordinary backlog ordering unless the decision also crosses a controlled threshold. | Formal in predictive control; hybrid models connect it to adaptive product decisions. | atlas_synthesis
ROL-RISK-OWNER | Risk Owner | assurance | Monitors an assigned risk and ensures an agreed response is carried out. | Acts within the approved response and delegated risk thresholds. | Does not unilaterally approve baseline or funding changes. | Applies across approaches with different review cadences. | atlas_synthesis
ROL-ISSUE-OWNER | Issue or Impediment Owner | delivery | Drives resolution of a current problem or blocker. | Coordinates resolution within assigned limits. | Assignment does not confer authority to alter controlled commitments. | In Scrum, impediment removal may be enabled by the Scrum Master while ownership remains with the person able to resolve it. | atlas_synthesis
ROL-PROCUREMENT-AUTHORITY | Procurement or Contract Authority | commercial | Conducts commercial actions and protects contractual rights and obligations. | Makes sourcing and contract decisions within delegated commercial authority. | Project personnel do not direct unilateral contract changes without this authority. | Applies across delivery approaches whenever external agreements are used. | atlas_synthesis
ROL-SELLER | Seller or Supplier | commercial | Delivers contracted products or services and evidence. | Controls its internal delivery within the agreement; contractual changes require authorized parties. | Does not own customer acceptance or buyer governance decisions. | May use predictive, adaptive, or hybrid methods subject to the agreement. | atlas_synthesis
ROL-OPERATIONS-OWNER | Operations or Service Owner | transition | Receives and sustains an operational capability after transition. | Decides operational readiness and receipt within delegated service authority. | Operational readiness is distinct from technical verification, customer acceptance, and project closure. | Applies across approaches; transition may be phased by release or performed at a major handoff. | atlas_synthesis
ROL-BENEFIT-OWNER | Benefit Owner | value | Owns realization and measurement of benefits after outputs enter use. | Makes operational benefit decisions within the receiving governance model. | Project closure can precede full benefit realization when ownership is explicitly transferred. | Applies across approaches and often extends beyond the project lifecycle. | atlas_synthesis
ROL-STAKEHOLDER | Stakeholder | value | Provides needs, constraints, feedback, influence, or affected-party perspective. | Varies; stakeholder status alone does not grant approval authority. | A request is not an authorized change solely because it comes from an influential stakeholder. | Engagement cadence varies across approaches. | atlas_synthesis
ROL-TEAM-MEMBER | Project Team Member | delivery | Performs assigned project work and contributes expertise and evidence. | Makes work decisions within assigned responsibilities and team agreements. | Generic predictive or hybrid role label; do not substitute it for the three Scrum accountabilities when explaining Scrum. | Common predictive and hybrid term. | atlas_synthesis
ROL-BUSINESS-ANALYST | Business Analyst | value | Elicits, analyzes, and traces needs and requirements. | Recommends and maintains requirement information within delegated product or project governance. | Does not automatically own product priority or formal acceptance. | May support predictive requirements baselines, adaptive backlog refinement, or both in hybrid work. | atlas_synthesis
ROL-KNOWLEDGE-OWNER | Knowledge or Records Custodian | assurance | Maintains controlled project knowledge, records, and archive integrity. | Controls record administration under organizational policy, not the underlying business decision. | Custody does not imply content approval or project ownership. | Applies across approaches and tools. | atlas_synthesis
ROL-KANBAN-SERVICE-TEAM | Kanban Service Team | flow | Manages and improves the flow of work through an existing service or workflow. | Uses existing organizational decision rights unless explicit policies delegate additional flow decisions. | Kanban does not require replacing existing roles or titles with a prescribed accountability set. | Kanban is applied to an existing way of working and can coexist with predictive, adaptive, or hybrid governance. | verified_official

## Process Role Map
ServiceBridge Modernization — illustrative Atlas working reference
Process ID | Process | Group | Lead | Performers | Contributors | Decision authority | Output owners | Approval or acceptance | Escalates to
PRC-DEVELOP-PROJECT-CHARTER | Develop Project Charter | Initiating | Sponsor | Project Manager; Sponsor | Subject-Matter Expert; Stakeholder | Sponsor | Sponsor | Sponsor | Sponsor
PRC-IDENTIFY-STAKEHOLDERS | Identify Stakeholders | Initiating | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Business Analyst | Project Manager | Project Manager |  | Sponsor
PRC-DEVELOP-PROJECT-MANAGEMENT-PLAN | Develop Project Management Plan | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-PLAN-SCOPE-MANAGEMENT | Plan Scope Management | Planning | Project Manager | Project Manager; Project Team Member; Business Analyst; Delivery Team | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Product Owner | Project Manager | Project Manager |  | Sponsor
PRC-COLLECT-REQUIREMENTS | Collect Requirements | Planning | Project Manager | Project Manager; Project Team Member; Business Analyst; Delivery Team | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Product Owner | Project Manager | Project Manager |  | Sponsor
PRC-DEFINE-SCOPE | Define Scope | Planning | Project Manager | Project Manager; Project Team Member; Business Analyst; Delivery Team | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Product Owner | Project Manager | Project Manager |  | Sponsor
PRC-CREATE-WBS | Create WBS | Planning | Project Manager | Project Manager; Project Team Member; Business Analyst; Delivery Team | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Product Owner | Project Manager | Project Manager |  | Sponsor
PRC-PLAN-SCHEDULE-MANAGEMENT | Plan Schedule Management | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-DEFINE-ACTIVITIES | Define Activities | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-SEQUENCE-ACTIVITIES | Sequence Activities | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-ESTIMATE-ACTIVITY-DURATIONS | Estimate Activity Durations | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-DEVELOP-SCHEDULE | Develop Schedule | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-PLAN-COST-MANAGEMENT | Plan Cost Management | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-ESTIMATE-COSTS | Estimate Costs | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-DETERMINE-BUDGET | Determine Budget | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-PLAN-QUALITY-MANAGEMENT | Plan Quality Management | Planning | Project Manager | Project Manager; Project Team Member; Quality Authority; Delivery Team | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Quality Authority |  | Sponsor
PRC-PLAN-RESOURCE-MANAGEMENT | Plan Resource Management | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Functional or Resource Manager; Delivery Team | Project Manager | Project Manager |  | Sponsor
PRC-ESTIMATE-ACTIVITY-RESOURCES | Estimate Activity Resources | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Functional or Resource Manager; Delivery Team | Project Manager | Project Manager |  | Sponsor
PRC-PLAN-COMMUNICATIONS-MANAGEMENT | Plan Communications Management | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-PLAN-RISK-MANAGEMENT | Plan Risk Management | Planning | Project Manager | Project Manager; Project Team Member; Risk Owner | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Risk Owner |  | Sponsor
PRC-IDENTIFY-RISKS | Identify Risks | Planning | Project Manager | Project Manager; Project Team Member; Risk Owner | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Risk Owner |  | Sponsor
PRC-PERFORM-QUALITATIVE-RISK-ANALYSIS | Perform Qualitative Risk Analysis | Planning | Project Manager | Project Manager; Project Team Member; Risk Owner | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Risk Owner |  | Sponsor
PRC-PERFORM-QUANTITATIVE-RISK-ANALYSIS | Perform Quantitative Risk Analysis | Planning | Project Manager | Project Manager; Project Team Member; Risk Owner | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Risk Owner |  | Sponsor
PRC-PLAN-RISK-RESPONSES | Plan Risk Responses | Planning | Project Manager | Project Manager; Project Team Member; Risk Owner | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Risk Owner |  | Sponsor
PRC-PLAN-PROCUREMENT-MANAGEMENT | Plan Procurement Management | Planning | Procurement or Contract Authority | Procurement or Contract Authority; Project Manager | Subject-Matter Expert; Stakeholder; Seller or Supplier; Compliance Authority | Procurement or Contract Authority | Procurement or Contract Authority | Procurement or Contract Authority | Sponsor; Governance Board
PRC-PLAN-STAKEHOLDER-ENGAGEMENT | Plan Stakeholder Engagement | Planning | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Business Analyst | Project Manager | Project Manager |  | Sponsor
PRC-DIRECT-AND-MANAGE-PROJECT-WORK | Direct and Manage Project Work | Executing | Project Manager | Project Manager; Delivery Team; Developers | Product Owner; Scrum Master; Subject-Matter Expert | Project Manager | Project Manager |  | Sponsor
PRC-MANAGE-PROJECT-KNOWLEDGE | Manage Project Knowledge | Executing | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-MANAGE-QUALITY | Manage Quality | Executing | Project Manager | Project Manager; Project Team Member; Quality Authority; Delivery Team | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Quality Authority |  | Sponsor
PRC-ACQUIRE-RESOURCES | Acquire Resources | Executing | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Functional or Resource Manager; Delivery Team | Functional or Resource Manager; Project Manager | Project Manager |  | Sponsor
PRC-DEVELOP-TEAM | Develop Team | Executing | Project Manager | Project Manager; Functional or Resource Manager; Project Team Member | Scrum Master; Developers | Project Manager | Project Manager |  | Sponsor
PRC-MANAGE-TEAM | Manage Team | Executing | Project Manager | Project Manager; Functional or Resource Manager; Project Team Member | Scrum Master; Developers | Project Manager | Project Manager |  | Sponsor
PRC-MANAGE-COMMUNICATIONS | Manage Communications | Executing | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-IMPLEMENT-RISK-RESPONSES | Implement Risk Responses | Executing | Project Manager | Project Manager; Project Team Member; Risk Owner | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Risk Owner |  | Sponsor
PRC-CONDUCT-PROCUREMENTS | Conduct Procurements | Executing | Procurement or Contract Authority | Procurement or Contract Authority; Project Manager | Subject-Matter Expert; Stakeholder; Seller or Supplier; Compliance Authority | Procurement or Contract Authority | Procurement or Contract Authority | Procurement or Contract Authority | Sponsor; Governance Board
PRC-MANAGE-STAKEHOLDER-ENGAGEMENT | Manage Stakeholder Engagement | Executing | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Business Analyst | Project Manager | Project Manager |  | Sponsor
PRC-MONITOR-AND-CONTROL-PROJECT-WORK | Monitor and Control Project Work | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-PERFORM-INTEGRATED-CHANGE-CONTROL | Perform Integrated Change Control | Monitoring and Controlling | Project Manager | Project Manager; Change Authority or CCB | Subject-Matter Expert; Stakeholder | Change Authority or CCB | Project Manager; Knowledge or Records Custodian | Change Authority or CCB | Sponsor; Governance Board
PRC-VALIDATE-SCOPE | Validate Scope | Monitoring and Controlling | Customer or Acceptance Authority | Project Manager; Customer or Acceptance Authority | Quality Authority; Delivery Team; Product Owner | Customer or Acceptance Authority | Project Manager | Customer or Acceptance Authority | Sponsor; Governance Board
PRC-CONTROL-SCOPE | Control Scope | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member; Business Analyst; Delivery Team | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Product Owner | Project Manager | Project Manager |  | Sponsor
PRC-CONTROL-SCHEDULE | Control Schedule | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-CONTROL-COSTS | Control Costs | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-CONTROL-QUALITY | Control Quality | Monitoring and Controlling | Quality Authority | Project Manager; Project Team Member; Quality Authority; Delivery Team | Subject-Matter Expert; Stakeholder; Compliance Authority | Quality Authority | Project Manager; Quality Authority | Quality Authority | Sponsor
PRC-CONTROL-RESOURCES | Control Resources | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Functional or Resource Manager; Delivery Team | Project Manager | Project Manager |  | Sponsor
PRC-MONITOR-COMMUNICATIONS | Monitor Communications | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder | Project Manager | Project Manager |  | Sponsor
PRC-MONITOR-RISKS | Monitor Risks | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member; Risk Owner | Subject-Matter Expert; Stakeholder; Compliance Authority | Project Manager | Project Manager; Risk Owner |  | Sponsor
PRC-CONTROL-PROCUREMENTS | Control Procurements | Monitoring and Controlling | Procurement or Contract Authority | Procurement or Contract Authority; Project Manager | Subject-Matter Expert; Stakeholder; Seller or Supplier; Compliance Authority | Procurement or Contract Authority | Procurement or Contract Authority | Procurement or Contract Authority | Sponsor; Governance Board
PRC-MONITOR-STAKEHOLDER-ENGAGEMENT | Monitor Stakeholder Engagement | Monitoring and Controlling | Project Manager | Project Manager; Project Team Member | Subject-Matter Expert; Stakeholder; Customer or Acceptance Authority; Business Analyst | Project Manager | Project Manager |  | Sponsor
PRC-CLOSE-PROJECT-OR-PHASE | Close Project or Phase | Closing | Project Manager | Project Manager; Project Team Member | Customer or Acceptance Authority; Operations or Service Owner; Benefit Owner; Procurement or Contract Authority; Knowledge or Records Custodian | Sponsor | Project Manager | Sponsor; Customer or Acceptance Authority; Operations or Service Owner | Governance Board

## Artifact Ownership
ServiceBridge Modernization — illustrative Atlas working reference
Artifact ID | Artifact | Creator | Owner or custodian | Contributors | Updater | Reviewer | Approver | Verifier | Acceptance authority | Receiving role
ART-QLT-001 | Quality Management Plan | Quality Authority; Delivery Team | Quality Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Quality Authority |  | Quality Authority
ART-QLT-002 | Quality Metrics | Quality Authority; Delivery Team | Quality Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Quality Authority |  | Quality Authority
ART-QLT-003 | Quality-Control Measurements | Quality Authority; Delivery Team | Quality Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Quality Authority |  | Quality Authority
ART-QLT-004 | Verified Deliverables | Quality Authority; Delivery Team | Quality Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Quality Authority |  | Quality Authority
ART-QLT-005 | Accepted Deliverables | Quality Authority; Delivery Team | Quality Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Quality Authority | Customer or Acceptance Authority | Quality Authority | Customer or Acceptance Authority
ART-REQ-001 | Requirements Documentation | Business Analyst; Project Manager | Project Manager; Knowledge or Records Custodian | Customer or Acceptance Authority; Product Owner; Stakeholder; Delivery Team | Project Manager; Project Team Member | Customer or Acceptance Authority; Product Owner
ART-REQ-002 | Requirements Traceability Matrix | Business Analyst; Project Manager | Project Manager; Knowledge or Records Custodian | Customer or Acceptance Authority; Product Owner; Stakeholder; Delivery Team | Project Manager; Project Team Member | Customer or Acceptance Authority; Product Owner
ART-PLN-001 | Project Management Plan | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-SCP-001 | Scope Baseline | Business Analyst; Project Manager | Project Manager; Knowledge or Records Custodian | Customer or Acceptance Authority; Product Owner; Stakeholder; Delivery Team | Project Manager; Project Team Member | Customer or Acceptance Authority; Product Owner
ART-STK-001 | Stakeholder Register | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-STK-003 | Stakeholder Engagement Assessment Matrix | Project Manager; Project Team Member | Project Manager | Project Team Member; Stakeholder; Sponsor; Product Owner | Project Manager; Project Team Member | Project Manager
ART-STK-004 | Stakeholder Power–Interest Grid | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-RSK-001 | Risk Register | Project Manager; Risk Owner; Issue or Impediment Owner; Delivery Team | Risk Owner; Project Manager | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager; Compliance Authority
ART-INT-001 | Assumption Log | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-CHR-001 | Project Charter | Sponsor; Project Manager | Sponsor; Benefit Owner | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager | Sponsor
ART-SCP-002 | Project Scope Statement | Business Analyst; Project Manager | Project Manager; Knowledge or Records Custodian | Customer or Acceptance Authority; Product Owner; Stakeholder; Delivery Team | Project Manager; Project Team Member | Customer or Acceptance Authority; Product Owner
ART-INT-002 | Lessons Learned Register | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-DEL-001 | Deliverables | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-CHG-001 | Change Requests | Stakeholder; Project Manager; Delivery Team | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager; Change Authority or CCB | Change Authority or CCB
ART-SCH-004 | Project Schedule | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-SCH-005 | Schedule Baseline | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-CST-001 | Cost Estimates | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-CST-002 | Cost Baseline | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-PRC-003 | Agreements | Procurement or Contract Authority; Project Manager | Procurement or Contract Authority; Knowledge or Records Custodian | Seller or Supplier; Subject-Matter Expert; Compliance Authority | Project Manager; Project Team Member | Procurement or Contract Authority | Procurement or Contract Authority
ART-WPI-001 | Work Performance Information | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-WPR-001 | Work Performance Reports | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager
ART-BIZ-001 | Business Case | Sponsor; Project Manager | Sponsor; Benefit Owner | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager | Sponsor
ART-BEN-001 | Benefits Management Information | Sponsor; Project Manager | Sponsor; Benefit Owner | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager | Sponsor
ART-RSK-003 | Risk Report | Project Manager; Risk Owner; Issue or Impediment Owner; Delivery Team | Risk Owner; Project Manager | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager; Compliance Authority
ART-ISS-001 | Issue Log | Project Manager; Risk Owner; Issue or Impediment Owner; Delivery Team | Issue or Impediment Owner; Project Manager | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager; Compliance Authority
ART-ISS-002 | Impediment Record | Project Manager; Risk Owner; Issue or Impediment Owner; Delivery Team | Issue or Impediment Owner; Project Manager | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager; Compliance Authority
ART-CHG-004 | Change Log | Stakeholder; Project Manager; Delivery Team | Project Manager; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager; Change Authority or CCB
ART-QLT-006 | Quality Reports | Quality Authority; Delivery Team | Quality Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Quality Authority |  | Quality Authority
ART-QLT-007 | Test and Evaluation Documents | Quality Authority; Delivery Team | Quality Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Quality Authority |  | Quality Authority
ART-CMP-001 | Compliance Evidence and Traceability | Compliance Authority; Quality Authority | Compliance Authority; Knowledge or Records Custodian | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Compliance Authority |  | Compliance Authority
ART-PRC-004 | Procurement Strategy | Procurement or Contract Authority; Project Manager | Procurement or Contract Authority; Knowledge or Records Custodian | Seller or Supplier; Subject-Matter Expert; Compliance Authority | Project Manager; Project Team Member | Procurement or Contract Authority | Procurement or Contract Authority
ART-PRC-005 | Procurement Statement of Work | Procurement or Contract Authority; Project Manager | Procurement or Contract Authority; Knowledge or Records Custodian | Seller or Supplier; Subject-Matter Expert; Compliance Authority | Project Manager; Project Team Member | Procurement or Contract Authority | Procurement or Contract Authority
ART-PRC-006 | Source-Selection Criteria | Procurement or Contract Authority; Project Manager | Procurement or Contract Authority; Knowledge or Records Custodian | Seller or Supplier; Subject-Matter Expert; Compliance Authority | Project Manager; Project Team Member | Procurement or Contract Authority | Procurement or Contract Authority
ART-PRC-007 | Closed Procurement | Procurement or Contract Authority; Project Manager | Procurement or Contract Authority; Knowledge or Records Custodian | Seller or Supplier; Subject-Matter Expert; Compliance Authority | Project Manager; Project Team Member | Procurement or Contract Authority | Procurement or Contract Authority
ART-TRN-001 | Transition Package | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Operations or Service Owner; Delivery Team; Quality Authority; Compliance Authority | Project Manager; Project Team Member | Project Manager | Operations or Service Owner |  |  | Operations or Service Owner
ART-CLS-001 | Final Report | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Customer or Acceptance Authority; Operations or Service Owner; Benefit Owner; Procurement or Contract Authority | Project Manager; Project Team Member | Project Manager | Sponsor |  |  | Knowledge or Records Custodian; Operations or Service Owner
ART-CLS-002 | Formal Closure Record | Project Manager; Project Team Member | Project Manager; Knowledge or Records Custodian | Customer or Acceptance Authority; Operations or Service Owner; Benefit Owner; Procurement or Contract Authority | Project Manager; Project Team Member | Project Manager | Sponsor |  |  | Knowledge or Records Custodian; Operations or Service Owner
ART-BEN-002 | Benefits Handoff Record | Sponsor; Project Manager | Sponsor; Benefit Owner | Subject-Matter Expert; Stakeholder | Project Manager; Project Team Member | Project Manager | Sponsor; Benefit Owner |  |  | Benefit Owner

## Lifecycle Handoffs
ServiceBridge Modernization — illustrative Atlas working reference
Chapter | Moment | Outgoing evidence | Receiving role | Decision or acknowledgment | Escalation trigger
Conception and Authorization | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Integrated Planning | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Requirements and Scope | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Schedule, Resources, and Cost | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Quality | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Risk, Compliance, and Procurement | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Execution and Team Leadership | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Monitoring and Change | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation
Verification, Acceptance, Transition, and Closure | ServiceBridge stage or release boundary | Approved records, current evidence, exceptions, and open obligations | Tailor from the public lifecycle handoff panel | Record acceptance, readiness, or authorized conditions | Missing evidence, ownership, authority, or unresolved obligation

## Decision Authority
ServiceBridge Modernization — illustrative Atlas working reference
Guide | Acts first | Decision authority | Approves or rejects | Escalates to | Scenario note
A Deliverable Fails Quality Inspection | Quality Authority; Delivery Team | Quality Authority; Project Manager; Change Authority or CCB | Quality Authority; Change Authority or CCB | Sponsor; Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.
A Verified Deliverable Is Rejected During Acceptance | Project Manager; Customer or Acceptance Authority | Customer or Acceptance Authority; Quality Authority; Change Authority or CCB | Customer or Acceptance Authority | Sponsor; Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.
A Risk Occurs or an Impediment Exceeds Team Authority | Risk Owner; Issue or Impediment Owner; Delivery Team | Project Manager; Product Owner; Compliance Authority | Project Manager; Product Owner | Sponsor; Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.
A Stakeholder Requests a Baseline Change | Stakeholder; Project Manager | Change Authority or CCB | Change Authority or CCB | Sponsor; Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.
A Compliance Problem Is Discovered | Delivery Team; Compliance Authority | Compliance Authority; Procurement or Contract Authority; Change Authority or CCB | Compliance Authority | Sponsor; Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.
Seller Performance Threatens Project Objectives | Procurement or Contract Authority; Project Manager | Procurement or Contract Authority | Procurement or Contract Authority | Sponsor; Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.
Transition or Closure Is Requested with Unresolved Obligations | Project Manager; Operations or Service Owner | Operations or Service Owner; Sponsor | Operations or Service Owner; Sponsor; Customer or Acceptance Authority | Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.
Expected Benefits Are Not Yet Realized at Project Closure | Project Manager; Benefit Owner | Sponsor; Benefit Owner | Sponsor; Benefit Owner | Governance Board | Record the decision, rationale, evidence, conditions, and follow-through for ServiceBridge Modernization.

## Assignment Workshop
ServiceBridge Modernization — illustrative Atlas working reference
Workstream or decision | Assigned role | Named person or group | Responsible | Accountable | Consulted | Informed | Authority limit | Evidence or artifact | Review date
ServiceBridge customer portal release | Product Owner | Avery Chen | Yes | Yes | Delivery Team; Customer | Sponsor; PMO | Backlog order within approved release funding | Product Backlog and release forecast | 2026-09-15
Production readiness | Operations or Service Owner | Morgan Lee | Yes | Yes | Quality and Compliance Authorities | Sponsor; Customer | Accept operational handoff with documented conditions | Transition Package | 2026-11-20

## Decision & Escalation
ServiceBridge Modernization — illustrative Atlas working reference
Decision ID | Situation | Acts first | Deciding role | Approval or rejection | Threshold | Escalates to | Evidence | Decision | Owner | Due date | Status
SBM-DEC-001 | Customer requests analytics after release baseline approval | Project Manager | Change Authority or CCB | Approve, reject, or defer | Baseline, funding, or release commitment affected | Sponsor | Impact analysis and Change Request | Pending | Avery Chen | 2026-09-22 | Open

## Approach Comparison
ServiceBridge Modernization — illustrative Atlas working reference
Topic | Predictive | Adaptive or Scrum | Hybrid
Planning and work | Project manager integrates formally planned work and functional assignments. | Product Owner orders value; Developers self-manage Sprint work; Scrum Master enables effectiveness. | Delivery decisions remain local while project integration reconciles dependencies and forecasts.
Change | Named change authority decides controlled baseline changes. | Product Owner can reorder backlog within product authority; not every reprioritization is a baseline change. | Explicit thresholds distinguish backlog flexibility from controlled change.
Quality and acceptance | Quality authority verifies; customer or acceptance authority accepts. | Definition of Done creates transparency for the Increment; formal acceptance remains explicit where required. | Iteration evidence feeds specialist verification and formal acceptance without duplicating records.
Roles | Titles and delegated responsibilities are commonly documented in plans and responsibility matrices. | Scrum has three accountabilities; Kanban respects the current role system. | Do not rename away authority boundaries; map accountabilities to governance decisions explicitly.