# Agreements — Filled Example

Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

# Shared fictional project

| Project | ServiceBridge Modernization |
| --- | --- |
| Organization | Northstar Public Services |
| Sponsor | Chief Customer Officer |
| Delivery model | Hybrid |
| Authorized budget | $2,400,000 |
| Target transition | 2027-11-19 |

# Predictive / Waterfall

The agreements supports an approved end-to-end plan, stage-gate review, and formal control of affected commitments.

| Parties and roles | Service Modernization Program Manager coordinates; Director of Customer Operations owns post-transition benefits |
| --- | --- |
| Scope and outcomes | Replace the outdated customer-service and appointment platform while preserving accessible service and auditable records |
| Commercial model | Predictive / Waterfall: Commercial model is recorded for ServiceBridge with an owner, current evidence, and the next decision. |
| Milestones | 2026-09-15 through 2027-12-17; transition target 2027-11-19 |
| Acceptance | Acceptance requires REQ-001 through REQ-005 evidence and authorization by the designated service owner |
| Change mechanism | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis |
| Compliance obligations | WCAG 2.2 AA, seven-year records retention, approved security controls, and contractual evidence obligations |
| Signatures or approval | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions |

# Adaptive / Agile

The agreements is maintained close to the work, refined from feedback, and reviewed at iteration or release cadence without removing governance.

| Parties and roles | Service Modernization Program Manager coordinates; Director of Customer Operations owns post-transition benefits |
| --- | --- |
| Scope and outcomes | Replace the outdated customer-service and appointment platform while preserving accessible service and auditable records |
| Commercial model | Adaptive / Agile: Commercial model is recorded for ServiceBridge with an owner, current evidence, and the next decision. |
| Milestones | 2026-09-15 through 2027-12-17; transition target 2027-11-19 |
| Acceptance | Acceptance requires REQ-001 through REQ-005 evidence and authorization by the designated service owner |
| Change mechanism | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis |
| Compliance obligations | WCAG 2.2 AA, seven-year records retention, approved security controls, and contractual evidence obligations |
| Signatures or approval | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions |

# Hybrid

The agreements connects baselined infrastructure and procurement commitments with incrementally refined software delivery.

| Parties and roles | Service Modernization Program Manager coordinates; Director of Customer Operations owns post-transition benefits |
| --- | --- |
| Scope and outcomes | Replace the outdated customer-service and appointment platform while preserving accessible service and auditable records |
| Commercial model | Hybrid: Commercial model is recorded for ServiceBridge with an owner, current evidence, and the next decision. |
| Milestones | 2026-09-15 through 2027-12-17; transition target 2027-11-19 |
| Acceptance | Acceptance requires REQ-001 through REQ-005 evidence and authorization by the designated service owner |
| Change mechanism | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis |
| Compliance obligations | WCAG 2.2 AA, seven-year records retention, approved security controls, and contractual evidence obligations |
| Signatures or approval | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions |

# Approach note

Adaptive delivery still plans, documents, governs, verifies, accepts, and manages benefits. The form and cadence are tailored; no backlog, board, or framework-specific record is treated as universal.