## Assumption Log
Assumption Log — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Assumption ID | Statement | Basis | Impact if false | Owner | Validation action | Due date | Status | Template note
ServiceBridge Modernization | Common across approaches | Seller integration capacity is available by 2027-02-01; procurement lead validates before build commitment | Active and controlled; current decision and next owner are recorded | Common across approaches: Basis is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Medium probability, high schedule and acceptance impact; priority 1 | Service Modernization Program Manager coordinates; Director of Customer Operations owns post-transition benefits | Common across approaches: Validation action is recorded for ServiceBridge with an owner, current evidence, and the next decision. | 2026-09-15 through 2027-12-17; transition target 2027-11-19 | Active and controlled; current decision and next owner are recorded | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Instructions
Assumption Log — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable assumption log workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.