## Change Log
Change Log — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Request ID | Summary | Analysis status | Decision | Decision authority | Baseline effect | Implementation status | Verification and closure | Template note
ServiceBridge Modernization | Predictive / Waterfall | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Predictive / Waterfall: Summary is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Active and controlled; current decision and next owner are recorded | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Predictive / Waterfall: Baseline effect is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Active and controlled; current decision and next owner are recorded | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Adaptive / Agile | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Adaptive / Agile: Summary is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Active and controlled; current decision and next owner are recorded | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Adaptive / Agile: Baseline effect is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Active and controlled; current decision and next owner are recorded | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Hybrid | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Hybrid: Summary is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Active and controlled; current decision and next owner are recorded | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Hybrid: Baseline effect is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Active and controlled; current decision and next owner are recorded | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Instructions
Change Log — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable change log workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.