## Obligations
Compliance Evidence and Traceability — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Obligation ID | Source | Requirement ID | Control or work item | Test ID | Evidence | Approval or exception | Retention rule | Template note
ServiceBridge Modernization | Common across approaches | WCAG 2.2 AA, seven-year records retention, approved security controls, and contractual evidence obligations | Customer Operations, accessibility obligation, and approved charter | REQ-003 — accessible, reliable customer service | Common across approaches: Control or work item is recorded for ServiceBridge with an owner, current evidence, and the next decision. | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | Controlled evidence package links requirement, test, decision, version, and seven-year retention rule | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Controlled evidence package links requirement, test, decision, version, and seven-year retention rule | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Evidence
Compliance Evidence Traceability — Evidence
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Evidence ID | Obligation ID | Description | Repository reference | Retention until | Owner
EVD-001 | OBL-001 | Independent WCAG audit report | Controlled repository/EVD-001 | 2034-11-19 | Compliance lead

## Verification
Compliance Evidence Traceability — Verification
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Verification ID | Obligation ID | Test ID | Result | Date | Authority
VER-001 | OBL-001 | TST-001 | Pass | 2027-10-10 | Compliance authority

## Exceptions
Compliance Evidence Traceability — Exceptions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Exception ID | Obligation ID | Rationale | Authority | Expiry | Status
EXC-001 | OBL-001 | No active exception | Compliance authority | 2027-11-19 | Closed

## Summary
Compliance Evidence Traceability — Summary
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Measure | Value
Obligations
Verified
Open exceptions

## Instructions
Compliance Evidence and Traceability — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable compliance evidence and traceability workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.