## Cost Baseline
Cost Baseline — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Control account or period | Time-phased budget USD | Management reserve excluded | Current forecast USD | Variance USD | Baseline version | Authority threshold | Change reference | Template note
ServiceBridge Modernization | Predictive / Waterfall | 2026-09-15 through 2027-12-17; transition target 2027-11-19 | $2,400,000 approved; CR-001 increases authorized funding by $80,000 | Predictive / Waterfall: Management reserve excluded is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Version 1.3, including approved CR-001 | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Adaptive / Agile | 2026-09-15 through 2027-12-17; transition target 2027-11-19 | $2,400,000 approved; CR-001 increases authorized funding by $80,000 | Adaptive / Agile: Management reserve excluded is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Version 1.3, including approved CR-001 | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Hybrid | 2026-09-15 through 2027-12-17; transition target 2027-11-19 | $2,400,000 approved; CR-001 increases authorized funding by $80,000 | Hybrid: Management reserve excluded is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Version 1.3, including approved CR-001 | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Summary
Cost Baseline — Summary
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Measure | Value USD
Time-phased baseline
Current forecast
Variance

## Assumptions
Cost Baseline — Assumptions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Assumption ID | Statement | Owner | Status
ASM-C02 | Management reserve is held outside the performance baseline | Sponsor | Approved

## Change History
Cost Baseline — Change History
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Change ID | Date | Amount USD | Decision
CR-001 | 2027-03-10 | 80000 | Approved

## Instructions
Cost Baseline — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable cost baseline workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.