## Issue Log
Issue Log — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Issue ID | Condition | Date identified | Impact and urgency | Owner | Action | Due date | Escalation and status | Template note
ServiceBridge Modernization | Common across approaches | ISS-001 — shared integration-test environment unavailable; platform lead restoring access by 2027-04-16 | Common across approaches: Condition is recorded for ServiceBridge with an owner, current evidence, and the next decision. | 2026-09-15 through 2027-12-17; transition target 2027-11-19 | Medium probability, high schedule and acceptance impact; priority 1 | Service Modernization Program Manager coordinates; Director of Customer Operations owns post-transition benefits | Common across approaches: Action is recorded for ServiceBridge with an owner, current evidence, and the next decision. | 2026-09-15 through 2027-12-17; transition target 2027-11-19 | Active and controlled; current decision and next owner are recorded | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Instructions
Issue Log — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable issue log workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.