## Quality-Control Measurements
Quality-Control Measurements — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Measurement ID | Deliverable ID | Requirement ID | Method | Expected result | Actual result | Status | Evidence reference | Template note
ServiceBridge Modernization | Common across approaches | Reduce median appointment-handling time by 30% within 12 months; operations dashboard is the data source | DEL-002 Accessible appointment portal | REQ-003 — accessible, reliable customer service | Traceable review, automated test where suitable, and authorized human decision | No critical accessibility findings; source and target control totals match with documented exceptions | Pass: zero critical accessibility defects and 100% control-total reconciliation for the sampled migration batch | Active and controlled; current decision and next owner are recorded | Controlled evidence package links requirement, test, decision, version, and seven-year retention rule | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Instructions
Quality-Control Measurements — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable quality-control measurements workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.