## Requirements
Requirements Traceability Matrix — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Requirement ID | Objective | Deliverable or work item | Verification method | Acceptance condition | Evidence | Status | Change reference | Template note
ServiceBridge Modernization | Predictive / Waterfall | REQ-001 — accessible, reliable customer service | Replace the outdated customer-service and appointment platform while preserving accessible service and auditable records | DEL-003 Migrated customer records | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | Acceptance requires REQ-001 through REQ-005 evidence and authorization by the designated service owner | Controlled evidence package links requirement, test, decision, version, and seven-year retention rule | Active and controlled; current decision and next owner are recorded | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Adaptive / Agile | REQ-001 — accessible, reliable customer service | Replace the outdated customer-service and appointment platform while preserving accessible service and auditable records | DEL-003 Migrated customer records | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | Acceptance requires REQ-001 through REQ-005 evidence and authorization by the designated service owner | Controlled evidence package links requirement, test, decision, version, and seven-year retention rule | Active and controlled; current decision and next owner are recorded | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Hybrid | REQ-001 — accessible, reliable customer service | Replace the outdated customer-service and appointment platform while preserving accessible service and auditable records | DEL-003 Migrated customer records | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | Acceptance requires REQ-001 through REQ-005 evidence and authorization by the designated service owner | Controlled evidence package links requirement, test, decision, version, and seven-year retention rule | Active and controlled; current decision and next owner are recorded | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Traceability
Requirements Traceability Matrix — Traceability
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Requirement ID | Source | Objective | Deliverable ID | Test ID | Acceptance ID | Status
REQ-001 | Charter | Accessible service | DEL-002 | TST-001 | ACC-001 | Verified

## Verification and Acceptance
Requirements Traceability Matrix — Verification and Acceptance
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Requirement ID | Verification method | Evidence reference | Decision | Decision date | Authority
REQ-001 | Independent WCAG audit | EVD-001 | Accepted | 2027-11-19 | Service owner

## Summary
Requirements Traceability Matrix — Summary
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Measure | Value
Requirements
Verified links

## Instructions
Requirements Traceability Matrix — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable requirements traceability matrix workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.