## Risk Register
Risk Register — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Risk ID | Cause-event-effect | Probability | Impact | Priority | Owner | Response | Trigger and status | Template note
ServiceBridge Modernization | Common across approaches | RSK-001 — migrated-record quality may delay acceptance; mitigate with rehearsal and reconciliation | Common across approaches: Cause-event-effect is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Medium probability, high schedule and acceptance impact; priority 1 | Medium probability, high schedule and acceptance impact; priority 1 | Medium probability, high schedule and acceptance impact; priority 1 | Service Modernization Program Manager coordinates; Director of Customer Operations owns post-transition benefits | Common across approaches: Response is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Active and controlled; current decision and next owner are recorded | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Scales
Risk Register — Scales
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Score | Probability | Impact | Response urgency
1 | Very low | Very low | Monitor
3 | Medium | Medium | Plan response
5 | Very high | Very high | Escalate

## Response Actions
Risk Register — Response Actions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Risk ID | Action ID | Action | Owner | Due date | Status
RSK-001 | RA-001 | Run migration rehearsal and reconcile control totals | Migration lead | 2027-06-30 | In progress

## Summary
Risk Register — Summary
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Measure | Value
Open risks
Priority 1 risks

## Instructions
Risk Register — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable risk register workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.