## Schedule Baseline
Schedule Baseline — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Baseline item | Approved start | Approved finish | Current forecast | Variance | Authority threshold | Baseline version | Change reference | Template note
ServiceBridge Modernization | Predictive / Waterfall | Predictive / Waterfall: Baseline item is recorded for ServiceBridge with an owner, current evidence, and the next decision. | 2026-09-15 | 2027-11-19 | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Version 1.3, including approved CR-001 | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Adaptive / Agile | Adaptive / Agile: Baseline item is recorded for ServiceBridge with an owner, current evidence, and the next decision. | 2026-09-15 | 2027-11-19 | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Version 1.3, including approved CR-001 | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
ServiceBridge Modernization | Hybrid | Hybrid: Baseline item is recorded for ServiceBridge with an owner, current evidence, and the next decision. | 2026-09-15 | 2027-11-19 | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Forecast remains within the CR-001 revised authorization; migration quality is the leading acceptance risk | Chief Customer Officer approves; specialized quality, procurement, compliance, and acceptance roles retain their decisions | Version 1.3, including approved CR-001 | CR-001 — stronger encryption; approved +$80,000 and +2 weeks after impact analysis | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Milestones
Schedule Baseline — Milestones
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Milestone ID | Milestone | Approved date | Current forecast | Variance days
MS-001 | Service transition | 2027-11-19 | 2027-11-19

## Dependencies
Schedule Baseline — Dependencies
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Item | Predecessor | Dependency type | Owner
Transition | Acceptance | Finish-to-start | Program manager

## Baseline Summary
Schedule Baseline — Baseline Summary
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Measure | Value
Baseline items
Items with variance

## Instructions
Schedule Baseline — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable schedule baseline workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.