## Test Cases
Test and Evaluation Documents — Filled Example
Filled ServiceBridge example; adapt before use. Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Project | Approach | Test ID | Requirement ID | Objective | Preconditions | Expected result | Actual result | Pass or fail | Evidence and defect | Template note
ServiceBridge Modernization | Common across approaches | REQ-001 accessibility audit and REQ-003 migration reconciliation must pass before acceptance | REQ-002 — accessible, reliable customer service | Replace the outdated customer-service and appointment platform while preserving accessible service and auditable records | Common across approaches: Preconditions is recorded for ServiceBridge with an owner, current evidence, and the next decision. | No critical accessibility findings; source and target control totals match with documented exceptions | Pass: zero critical accessibility defects and 100% control-total reconciliation for the sampled migration batch | Common across approaches: Pass or fail is recorded for ServiceBridge with an owner, current evidence, and the next decision. | Controlled evidence package links requirement, test, decision, version, and seven-year retention rule | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.

## Execution Results
Test Evaluation Documents — Execution Results
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Test ID | Run date | Tester | Result | Evidence | Defect ID
TST-001 | 2027-10-10 | Accessibility lead | Pass | EVD-001

## Defects
Test Evaluation Documents — Defects
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Defect ID | Test ID | Severity | Owner | Status | Retest result
DEF-001 | TST-002 | Medium | Portal team | Closed | Pass

## Summary
Test Evaluation Documents — Summary
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Measure | Value
Test cases
Passed
Failed

## Instructions
Test and Evaluation Documents — Instructions
Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Topic | Guidance
Purpose | Editable test and evaluation documents workbook for project-specific use.
How to use | Replace instructional placeholders, retain stable IDs, record owners and evidence, and keep decisions traceable.
Blank versus filled | The blank workbook contains structure and instructions only. The filled workbook uses the fictional ServiceBridge Modernization scenario.
Governance note | Illustrative Atlas resource; adapt it to organizational governance. PMI does not prescribe this form.
Accessibility | Use descriptive sheet names, meaningful headers, and do not rely on color alone to communicate status.