## Instructions
Project Quantitative Methods
Illustrative study workbook. Adapt it to organizational governance.
Workbook guidance
How to use | Yellow cells are editable inputs; blue cells contain formulas. All examples use the same units within a calculation.
Scope | Estimating, schedule network analysis, reserves and baselines, and earned value management.
Verification | Only formulas published by the Atlas registry are included. PERT variance and crash cost slope are withheld.
EVM boundary | PV, EV, and AC must use the same measured scope and status date. SV is a cost-unit measure, not calendar days.
Governance | Management reserve is outside BAC and does not authorize out-of-scope work.
Source | Canonical definitions: definitions/formulas.yaml; public reference: Formula and Quantitative Methods.

## Three-Point Estimating
Three-Point Estimating
Edit O, M, P, quantity, and rate. Results are formula-driven.
Measure | Input / result | Units | Expression | Status | Interpretation
Optimistic (O) | 8 | days
Most likely (M) | 12 | days
Pessimistic (P) | 20 | days
Triangular TE |  | days | TE = (O + M + P) / 3
Beta / PERT TE |  | days | TE = (O + 4M + P) / 6
PERT standard deviation |  | days | σ = (P - O) / 6
Parametric example
Quantity | 320 | records
Rate per unit | 1.5 | hours / record
Estimate |  | hours | Estimate = Quantity × Rate per unit

## Schedule Network
Schedule Network
Day-zero convention; edit durations only. Network is A → B/C → D.
Activity | Duration | Predecessors | ES | EF | Total Float
A · Confirm scope | 3 | — | 0 |  | 0
B · Configure service | 5 | A |  |  | 0
C · Prepare training | 3 | A |  |  | 2
D · Validate release | 4 | B, C |  |  | 0
Critical path | A → B → D |  | Project duration
Exam note | Inclusive-day questions may apply +1 or -1. Follow the question and never mix conventions.

## EVM Calculator
EVM Calculator
ServiceBridge Modernization status-date example.
Inputs
BAC | 2400000 | Interpretation
PV | 1200000 | EV is below PV and AC exceeds EV. If current CPI continues, forecast total cost is above BAC. SV is in dollars, not days.
EV | 1000000
AC | 1250000
Calculated measures
SV
SPI
CV
CPI
EAC (CPI continues)
ETC
VAC
TCPI (BAC)
TCPI (EAC)

## Reserves and Budget
Reserves and Budget
Contingency is inside the cost baseline; management reserve is outside BAC.
Aggregated cost estimates | 2200000 | BAC includes contingency reserve and excludes management reserve. Management reserve addresses unforeseen in-scope work, not unauthorized scope.
Contingency reserve | 200000
BAC / cost baseline
Management reserve | 150000
Total project budget

## Formula Reference
Verified Formula Reference
Generated from definitions/formulas.yaml; withheld formulas are excluded.
ID | Name | Expression | Units | Verification | Assumption
FRM-EST-001 | Parametric estimate | Estimate = Quantity × Rate per unit | Output uses the rate numerator unit; quantity and rate denominator must match. | verified_current_course | The rate is valid and scalable for the quantity and conditions.
FRM-EST-002 | Triangular three-point estimate | TE = (O + M + P) / 3 | Same time, effort, or cost unit as O, M, and P. | verified_current_course | O, M, and P use the same scope and units.
FRM-EST-003 | Beta / PERT three-point estimate | TE = (O + 4M + P) / 6 | Same time, effort, or cost unit as O, M, and P. | verified_current_course | O, M, and P use the same scope and units and a beta approximation is appropriate.
FRM-EST-004 | PERT standard deviation | σ = (P - O) / 6 | Same unit as P and O. | verified_official_pmi | The PERT beta approximation and comparable endpoints are appropriate.
FRM-SCH-001 | Early finish | EF = ES + Duration | Consistent time units. | verified_official_pmi | Finish-to-start logic without lag unless the network states otherwise.
FRM-SCH-002 | Late start | LS = LF - Duration | Consistent time units. | verified_official_pmi | The required finish and successor logic are established.
FRM-SCH-003 | Total float from start dates | Total Float = LS - ES | Time units. | verified_current_course | Early and late dates use the same convention and calendars.
FRM-SCH-004 | Total float from finish dates | Total Float = LF - EF | Time units. | verified_current_course | Early and late dates use the same convention and calendars.
FRM-SCH-005 | Free float | Free Float = earliest ES of immediate successors - EF | Time units. | verified_official_pmi | Use the earliest ES when there are multiple immediate successors.
FRM-RES-001 | Cost baseline / BAC | BAC = aggregated cost estimates + contingency reserves | Currency. | verified_current_course | Scope and reserve treatment are authorized under project governance.
FRM-RES-002 | Total project budget | Total Project Budget = BAC + management reserve | Currency. | verified_current_course | Management reserve is governed and not used for unauthorized out-of-scope work.
FRM-EVM-001 | Schedule variance | SV = EV - PV | Currency or other budget units. | verified_current_course | EV and PV cover the same measured scope and status date.
FRM-EVM-002 | Schedule performance index | SPI = EV / PV | Dimensionless ratio. | verified_current_course | PV is nonzero and scope/status date are aligned.
FRM-EVM-003 | Cost variance | CV = EV - AC | Currency or other budget units. | verified_current_course | EV and AC cover the same measured scope and status date.
FRM-EVM-004 | Cost performance index | CPI = EV / AC | Dimensionless ratio. | verified_current_course | AC is nonzero and scope/status date are aligned.
FRM-EVM-005 | Estimate at completion — current CPI continues | EAC = BAC / CPI | Currency. | verified_current_course | Current cumulative cost efficiency is expected to continue for the remaining work; CPI is nonzero.
FRM-EVM-006 | Estimate to complete | ETC = EAC - AC | Currency. | verified_current_course | EAC and AC use the same measured scope and status date.
FRM-EVM-010 | Variance at completion | VAC = BAC - EAC | Currency. | supplemental_official_pmi | BAC and EAC cover the same measured scope.
FRM-EVM-011 | To-complete performance index against BAC | TCPI(BAC) = (BAC - EV) / (BAC - AC) | Dimensionless ratio. | supplemental_official_pmi | BAC minus AC is positive and BAC remains the selected target.
FRM-EVM-012 | To-complete performance index against approved EAC | TCPI(EAC) = (BAC - EV) / (EAC - AC) | Dimensionless ratio. | supplemental_official_pmi | EAC minus AC is positive and EAC is the selected approved target.
FRM-COM-001 | Potential communication channels | C = n(n - 1) / 2 | Potential pairwise paths. | supplemental_official_pmi | n is an integer of at least 1; direction is not counted separately; the measure represents potential interpersonal paths rather than messages, technologies, methods, or required direct communications.